## Executive Summary
THE SIGNAL — Functionality Scope Assessment
Project status review for production · Generated 2026-06-23 · Phase: Campaign Build (post vertical-slice)
BOTTOM LINE
The game's core systems are built and were proven in the original vertical slice: first-person player, combat with three enemy types, weapons (gun / melee / grenade), grid inventory, save/load (player state, current level, dialogue history, story flags and collected notes across slots), interaction, locks & puzzles, dialogue, HUD, menus, and a working signature danger-sense audio mechanic. The project's frontier now is CONTENT and LEVELS, not core tech: real objectives, narrative and conversations still need authoring, and the campaign maps are mostly unbuilt (only one floor is actively being built; several areas do not exist yet). Two whole feature areas are greenfield: environmental hazards and cinematic cutscenes. No formal end-to-end QA playthrough has happened yet — current statuses reflect what is BUILT, not what has been play-tested.
FUNCTIONALITY READINESS AT A GLANCE
Lens | Done | In Progress | Needed / Not Built | Out of scope (N/A)
Capability checks (73 from QA list) | 27 | 26 | 14 | 6
Game systems / features (36) | 23 | 8 | 4 | 0
Rough readiness of in-scope functionality: ~60% (capability checks, counting In-Progress as half). Systems readiness: ~77%.
WHERE EACH AREA STANDS
Area | Overall | One-line read
Level Design | In Progress | Door/puzzle/minimap tools done; campaign levels mostly unbuilt, no full playthrough.
Environmental System | Not Built | Greenfield — no hazards (fire/void/tentacles) exist yet; health pipeline ready for them.
Quest & Objective System | In Progress | Engine works; real quests, on-screen markers, branching and save-persistence still needed.
Progression / Inventory / Save | In Progress | Inventory and save/load (player state, story flags, dialogue, notes, multi-slot) are done; only healing consumables missing.
Narrative / Story System | In Progress | Readable notes + branching dialogue/story-flags built and saved; no cutscenes; story content still to author.
NPC & Character System | In Progress | Talking to NPCs + enemy states fully work; campaign conversations still need writing.
Combat System | In Progress | Largely done — 3 enemies, full weapon set, death/respawn; no enemy loot drops; needs balance + QA.
Audio System | In Progress | Strong core incl. signature danger-sense; needs voice acting, area/combat music, options & mix.
RECOMMENDED PRIORITY ORDER (production view)
1. Lock a campaign vertical-slice: build at least one area end-to-end (incl. interior lighting) so there is one full, playable path.
2. Run the first formal QA playthrough of a built area — convert 'built' into 'tested' (softlocks, reachability, transitions).
3. Author real content on the proven engines: objectives, in-world conversations, and found notes for the slice.
4. Combat balance pass + decide enemy loot-drops (today loot comes only from hand-placed containers).
5. Decide scope on the two greenfield areas: environmental hazards and cinematic cutscenes (both are zero today).
6. Finish objective-completion save persistence (story flags, dialogue and notes already save; this is the last save piece).
7. Audio content & polish: voice acting for spoken lines, area/combat music transitions, and a final mix pass.

## Functionality Scope
FUNCTIONALITY SCOPE — what is Done, In Progress, and still Needed (project-wide)
Status reflects what is BUILT in the project, not yet formally play-tested. 'Needed' = does not exist yet. 'N/A' = intentionally not part of this game's design.
Area | System | Capability / Test Case | Status | What this means (plain English)
LEVEL DESIGN — Overall: In Progress [ Done 2 · In Progress 10 · Needed 0 · N/A 0 ]
Level-building tools and interactive pieces (doors, vents, key/card locks, collision fixes, in-game minimap) are built and proven in the original demo area. The actual campaign levels are still mid-construction: one office floor is actively being sculpted, other buildings and floors do not exist yet, interior lighting in the office is not placed, and per-floor maps still need generating. Treat door and puzzle mechanics as built, but the campus itself as a work in progress with no full playthrough or QA pass yet.
LVL-01 | Level Design | Player can reach every intended area | In Progress | Door, gate and vent connections are built, but most campaign areas do not exist yet, so full-campus reachability cannot be confirmed.
LVL-02 | Level Design | All room-to-room transitions work both ways | In Progress | Doors open from either side and a level-to-level transit ride works; broader room-to-room flow is unbuilt and unverified across the campaign.
LVL-03 | Level Design | No gaps/holes/seams to fall through | In Progress | A tool exists to seal fall-through floors from asset packs, but it must be run per level and the campaign levels are unfinished and untested.
LVL-04 | Level Design | Collision blocks out-of-bounds travel | In Progress | Tooling fixes invisible-wall and missing-collision issues on purchased meshes, but out-of-bounds blocking is only verified in the old demo, not new levels.
LVL-05 | Level Design | All doors, gates, connections open/close as designed | Done | Hinged and sliding doors, keycard gates, and screwdriver vents all open and close as designed and are proven in the demo area.
LVL-06 | Level Design | No clipping, floating props, or z-fighting | In Progress | No clipping or floating-prop audit has been done; levels are actively being sculpted, so this awaits a finished-art QA sweep.
LVL-07 | Level Design | Navmesh covers all walkable areas | In Progress | Enemies path on a navmesh that exists in the current office floor, but coverage of new areas is not yet verified as levels are still being built.
LVL-08 | Level Design | No softlocks — player can't get permanently stuck | In Progress | No softlock testing has occurred; campaign levels are unfinished and a final bug-sweep playthrough is still a planned task.
LVL-09 | Level Design | Environmental puzzles completable with intended solution | Done | Lock-and-key and screwdriver-vent puzzles are completable with their intended items and confirmed working in the demo area.
LVL-10 | Level Design | Puzzle state resets cleanly on retry/return | In Progress | Puzzles reset only when the level fully reloads; an opened vent is permanently gone with no return-and-retry, and door state is not saved.
LVL-11 | Level Design | Lighting sufficient to navigate every area | In Progress | The original demo area is lit, but the new office building currently has no interior lights placed, leaving large areas flashlight-only.
LVL-12 | Level Design | Landmarks/sightlines support orientation | In Progress | Floor-number signs and an in-game minimap aid orientation, but per-floor maps are not yet generated and sightline layout is still being authored.
ENVIRONMENTAL SYSTEM — Overall: Needed [ Done 0 · In Progress 0 · Needed 6 · N/A 2 ]
Environmental hazards do not exist in the game yet. No fire, gas, electrical, water, or biomass/void hazard can hurt or threaten the player. Today only enemies, the player's weapons, and the thrown grenade deal damage. The hazard art packs (Biomass, Muscle Tentacles, slime, void reskin) are still shopping-list tickets, not built features. Scripted dynamic level events and custom physics-object behavior also do not exist. This whole area is greenfield work for the campaign.
LVL-13 | Environmental System | Hazards deal correct damage/effect | Needed | No environmental hazards exist, so none deal damage. Only enemies, weapons, and grenades can hurt the player today.
LVL-14 | Environmental System | Fire spreads and extinguishes per rules | Needed | There is no fire hazard at all, so no spreading or extinguishing behavior is implemented.
LVL-15 | Environmental System | Void tendrils spawn, move, despawn per design | Needed | Void/biomass tendrils are only a planned art-pack ticket; nothing spawns, moves, or despawns in-game.
LVL-16 | Environmental System | Dynamic events trigger on correct conditions | Needed | No scripted dynamic-event system exists, so no events trigger on a schedule or conditions.
LVL-17 | Environmental System | Physics objects react believably | N/A | No custom physics hazards are designed; movable objects rely on the engine's default physics, which is generally stable.
LVL-18 | Environmental System | Hazards have clear visual/audio warning cues | Needed | With no hazards built, there are no visual or audio warning cues for them.
LVL-19 | Environmental System | Stacked environmental effects don't crater performance | N/A | No stacked environmental effects exist yet, so there is nothing to performance-test in this area.
LVL-20 | Environmental System | Player can avoid/counter/escape each hazard | Needed | Since no hazards exist, there is no avoid/counter/escape design or mechanic to evaluate.
QUEST & OBJECTIVE SYSTEM — Overall: In Progress [ Done 1 · In Progress 3 · Needed 4 · N/A 0 ]
The engine that runs quests works: a quest starts, its steps tick off in order, and the player sees the current goal in a top-corner tracker that pops up briefly. But almost no real quests are authored yet (only one placeholder test goal), quest progress is NOT saved between sessions, there are no on-screen markers pointing to where to go, and there is no concept of branching choices or failed/abandoned quests.
QST-01 | Quest & Objective System | Quests start on the correct trigger | In Progress | Quests can start automatically at game start or be triggered by in-world events; one placeholder quest auto-starts. Real triggers per level still need authoring.
QST-02 | Quest & Objective System | Objectives track progress as steps complete | In Progress | Step-by-step progress tracks correctly via flags and order; but item/dialogue/note/reach triggers auto-completing steps are not yet hooked up.
QST-03 | Quest & Objective System | Branching paths route to correct outcomes | Needed | Quests advance in a fixed sequence only. There is no concept of branching paths leading to different outcomes.
QST-04 | Quest & Objective System | Completion states register and persist | In Progress | Objectives complete and unlock in order; saving completed-objective state across a reload is the final piece being wired.
QST-05 | Quest & Objective System | Quest log shows current objective & progress | Done | On-screen tracker shows the current quest and its steps, updates on every change, and reappears briefly after menus close.
QST-06 | Quest & Objective System | Mutually-exclusive choices lock out alternatives | Needed | There is no mechanism for choices that lock out alternatives; the system has no concept of mutually-exclusive options.
QST-07 | Quest & Objective System | Failed/abandoned quests handled gracefully | Needed | Quests can only be active or complete; there is no fail or abandon state, so this scenario is not yet handled.
QST-08 | Quest & Objective System | Objective markers point to correct location | Needed | No on-screen markers or waypoints point the player toward objective locations; the in-game map shows only doors and the player.
PROGRESSION / INVENTORY / SAVE — Overall: In Progress [ Done 6 · In Progress 1 · Needed 0 · N/A 0 ]
Inventory (carry, drop, stack, ammo) and the save/load system both work and were proven in the slice. Manual save terminals write the player's position and health, the current level, dialogue history, story flags and every collected note across multiple slots, and loading restores them. The remaining gap is content, not tech: there are no healing-type consumable items yet, and a formal repeated-save / slot-isolation QA pass has not been run.
QST-09 | Progression / Inventory / Save | Inventory add/remove/stack behaves correctly | Done | Picking up, dropping, and stacking items in the bag works and was confirmed in play during the slice.
QST-10 | Progression / Inventory / Save | Item use consumes correct qty & applies effects | In Progress | Ammo and grenades are used up in the exact right amount, but no health/consumable items that get used up exist yet.
QST-11 | Progression / Inventory / Save | Save writes all relevant player/world state | Done | Saving captures the player's position and health, current level, dialogue history, story flags and all collected notes.
QST-12 | Progression / Inventory / Save | Load accurately restores all saved state | Done | Loading restores the saved player position, health, level, dialogue history, story flags and notes.
QST-13 | Progression / Inventory / Save | Checkpoints trigger at the correct points | Done | Manual save terminals work and death returns the player to their last checkpoint; per-level placement is content work.
QST-14 | Progression / Inventory / Save | Repeated save/load doesn't corrupt data | Done | Save/load is functional; a formal repeated-cycle stress test still remains, as with all features.
QST-15 | Progression / Inventory / Save | Multiple save slots stay isolated | Done | Multiple save slots are supported, each with its own screenshot, location, playtime and date.
NARRATIVE / STORY SYSTEM — Overall: In Progress [ Done 3 · In Progress 2 · Needed 2 · N/A 0 ]
Found readable logs/notes and a branching dialogue + story-flag engine are built and functional, and dialogue history, story flags and collected notes ARE written to the save file. Cutscenes do not exist at all. The main gap is authored content: only test dialogues and two sample notes exist so far, so branching and continuity are unproven in a real playthrough.
NAR-01 | Narrative / Story System | Cutscenes play at correct triggers | Needed | There are no cutscenes in the game yet, so nothing plays at story triggers. Cinematics are a future task.
NAR-02 | Narrative / Story System | Cutscenes skippable & resume gameplay cleanly | Needed | Since no cutscenes exist, there is nothing to skip or resume from. This is gated on building cinematics first.
NAR-03 | Narrative / Story System | Logs/lore items collectible and readable | Done | Players can pick up notes and logs and read them in a dedicated notes screen; collected notes persist permanently. Real sample notes exist.
NAR-04 | Narrative / Story System | Branching story states persist across save | Done | Story choices, dialogue history and collected notes are saved and restored, so branching story state survives across a save/load.
NAR-05 | Narrative / Story System | Story flags set/clear at correct moments | Done | A story-flag (narrative beat) system sets and clears flags from dialogue/events and writes them into the save file.
NAR-06 | Narrative / Story System | No narrative continuity errors from choices | In Progress | Choice-driven branching is built and gates options correctly, but with only placeholder dialogue authored, continuity across real choices is untested.
NAR-07 | Narrative / Story System | Cutscene audio and subtitles stay in sync | In Progress | For spoken dialogue, voice audio and subtitles are timed to play together. No cutscene audio exists yet to sync separately.
NPC & CHARACTER SYSTEM — Overall: In Progress [ Done 5 · In Progress 1 · Needed 0 · N/A 3 ]
Talking to NPCs works end-to-end: prompts, branching conversations, player choices that set story flags, subtitles, lip-sync, and a one-time-only option. Enemies have real behavior states (calm, alerted, hunting, attacking) driven by sight and distance. What's missing is authored conversation content for the campaign and a custom-styled dialogue box. A relationship-points system and NPC daily schedules are deliberately not part of this game's design.
NAR-08 | NPC & Character System | Character states transition correctly (idle/alert/hostile) | Done | Enemies move correctly between calm, alerted, chasing, and attacking states; friendly NPCs face the player and gesture while talking.
NAR-09 | NPC & Character System | Dialogue trees branch to correct nodes | Done | Conversations branch to the right follow-up based on the player's choice; the dialogue engine handles jumps and conditional options. Needs authored content.
NAR-10 | NPC & Character System | Dialogue choices produce intended consequences | Done | Player choices fire story flags and can redirect the conversation, so picks have real consequences. Content authoring still pending.
NAR-11 | NPC & Character System | Relationship values update on player actions | N/A | This game has no relationship-points system; the trust theme is narrative and explicitly unspecified in design. No such stat to update.
NAR-12 | NPC & Character System | Relationship thresholds trigger behavior changes | N/A | No relationship-score thresholds exist; design states no RPG-style systems. Behavior changes come from story flags, not numeric relationship levels.
NAR-13 | NPC & Character System | Behavior responds to player proximity/actions | Done | Enemies respond to how close the player is and whether they can see them: distance and line-of-sight trigger alert, chase, and attack.
NAR-14 | NPC & Character System | No dialogue dead-ends/loops/unreachable branches | In Progress | The engine cleanly ends or continues conversations and hides locked options, but there is no automated tool to catch dead-ends or loops in authored content.
NAR-15 | NPC & Character System | Subtitles match spoken/written dialogue | Done | Subtitles display the exact authored line text paired with its voice clip, so on-screen text matches the spoken line by design.
NAR-16 | NPC & Character System | NPC schedules/routines run on correct conditions | N/A | NPCs do not roam on schedules in this game; they stay put for dialogue. No daily-routine system exists or is planned.
COMBAT SYSTEM — Overall: In Progress [ Done 8 · In Progress 3 · Needed 1 · N/A 1 ]
Combat is largely built and functional: three enemy types hunt and attack the player, guns/melee/grenades deal damage with weak-point and headshot bonuses, enemies die and clean up, and player death fades out and restarts the area. The biggest missing piece is enemies dropping loot on death (no such system exists - loot only comes from hand-placed containers). Damage numbers and detection ranges are designer-adjustable but still placeholder values, so a tuning pass and a formal QA playthrough remain.
CMB-01 | Combat System | Enemy AI detects player within aggro range | Done | All three enemy types notice the player at set distances and only react when they have a clear line of sight, so walls keep you hidden.
CMB-02 | Combat System | Enemy pathing avoids obstacles, reaches player | Done | Ground enemies path around obstacles to reach the player and stop at closed doors; the wall-ambush enemy lunges and chases on a direct line instead.
CMB-03 | Combat System | Damage values match design spec | In Progress | Every weapon and enemy attack has its own adjustable damage number, but the current values are placeholder defaults awaiting a balance pass.
CMB-04 | Combat System | Critical hits & multipliers apply correctly | Done | Headshots and close-range weak-point hits deal extra damage, grenades hit harder at the center of the blast, and a damage-multiplier system works.
CMB-05 | Combat System | Weapon switching responsive, correct equipped state | Done | Switching weapons swaps the held item and updates the on-screen weapon icon and ammo display; fire input is blocked during the swap animation.
CMB-06 | Combat System | Ammo/durability/cooldown deplete & refill per design | Done | Ammo depletes when firing, reloads from a capped reserve, and fire rate is gated by a cooldown; grenades stack and deplete. Pickup caps work.
CMB-07 | Combat System | Hit detection accurate (no phantom/missed hits) | Done | Shots and melee swings use accurate aimed traces that pass through doorway trigger zones, a documented fix for bullets being eaten near doors.
CMB-08 | Combat System | Loot drops at intended rates | Needed | Enemies do not drop loot when killed. Loot exists only in hand-placed containers and pickups, so there are no drop rates to tune yet.
CMB-09 | Combat System | Dropped loot spawns visibly & is pickable | N/A | There are no enemy loot drops to spawn or pick up. World pickups and containers are placed and lootable, but that is the inventory system, not combat drops.
CMB-10 | Combat System | Enemy death: correct anim, cleanup, despawn | Done | On death enemies stop moving, turn off collision, play a death animation, settle as a corpse, and the wall creature cleans itself up after a delay.
CMB-11 | Combat System | Combat works in tight and open spaces | In Progress | Enemy logic is space-agnostic and traces account for walls and doorways, but tight-vs-open-space behavior has not been confirmed by a full playthrough.
CMB-12 | Combat System | Multiple enemies behave without AI breakdown | In Progress | Each enemy runs its own self-contained brain on a registry, so multiples should coexist, but a many-enemies stress test has not been confirmed.
CMB-13 | Combat System | Player death triggers fail/respawn flow | Done | When the player dies from combat the screen fades to black and the area reloads after a short delay, restoring full health on respawn.
AUDIO SYSTEM — Overall: In Progress [ Done 2 · In Progress 6 · Needed 1 · N/A 0 ]
The core audio plumbing is genuinely built and impressive: enemy growls/attacks, weapon and melee impacts, footsteps, and the signature phone-interference warning all fire on real in-game events, and sounds are positioned in 3D with wall-muffling. The standout feature, the phone earbud-interference mechanic, is fully coded and reacts smoothly to how close danger is. What remains is content and polish: no recorded character voice acting yet, music does not change between areas or during combat, there is no player options screen to set or save volume, and a final ship-quality mix pass is still pending.
AUD-01 | Audio System | SFX play on correct triggers | In Progress | Enemy, weapon, melee, and footstep sounds reliably play on the right in-game events; content polish still pending.
AUD-02 | Audio System | Music transitions between areas & combat | In Progress | Background ambience plays in sparse fade in/out loops, but music does not switch by area or shift during combat.
AUD-03 | Audio System | Earbud interference triggers under right conditions | In Progress | The phone interference warning correctly triggers from danger zones and enemy proximity; in-world placement and tuning ongoing.
AUD-04 | Audio System | Earbud interference intensity scales with driver | Done | Interference loudness and the on-screen waveform scale smoothly with how close the player is to the danger source.
AUD-05 | Audio System | Voice lines play fully (no overlap/cutoff/double-fire) | In Progress | Dialogue voice playback stops cleanly when interrupted so lines do not overlap, but no actual voice lines are recorded yet.
AUD-06 | Audio System | Audio mix balanced (SFX vs music vs voice) | In Progress | Audio routing buses and reverb exist and per-sound levels are set, but a final balanced ship-quality mix pass is still open.
AUD-07 | Audio System | Spatial/3D audio direction matches source | Done | Enemy sounds come from their actual location in 3D space with distance falloff and muffling through walls; phone/music are intentionally 2D.
AUD-08 | Audio System | No missing or placeholder audio in shipped content | In Progress | Custom-produced sounds exist for creatures, weapons, phone, and footsteps, but voice acting is missing and a no-placeholder final pass remains.
AUD-09 | Audio System | Volume/mute settings apply and persist | Needed | There is no in-game options screen to adjust or mute volume, and no saved volume settings; this is planned but not yet built.

## Systems Readiness
SYSTEMS READINESS — the full feature inventory (concise build-state of every system)
A tighter index than the session log: every notable gameplay/technical system and where it stands.
System | Category | Status | What the player gets / what it does
Death & Respawn | Player | Done | When the player dies they get a death transition and respawn back at their last checkpoint.
First-Person Player Character | Player | Done | Player walks, looks, sprints, crouches, leans and peeks around cover with full first-person arms and body.
Ladder Climbing | Player | Done | Player can mount and climb ladders rung by rung with hands matching the rungs, and climb off at the top.
Controller / Gamepad Support | Player | In Progress | Xbox controller plays the game; on-screen prompt swapping and sensitivity options still remain.
Player Health & Damage Feedback | Combat | Done | Player has health that drops when hurt, shown on screen with a red damage flash on the edges.
Throwable Grenades | Combat | Done | Player can throw grenades that explode and damage nearby enemies, with a limited carried stack.
Weapon & Ranged Combat | Combat | Done | Player can fire guns, reload, and aim down sights; bullets hit enemies and leave marks on walls.
Melee Combat (Pipe) | Combat | In Progress | Player can swing a melee weapon that damages enemies; the swing look and timing still need polish.
Crawler Enemy (wall creature) | Enemies | Done | A tentacle creature that patrols, hunts, stalks, climbs walls, pounces and slams the player, then can be killed.
Scytheer Enemy (roaming attacker) | Enemies | In Progress | A roaming creature that wanders, alerts on sight, chases and does three attack swings; built but needs placement and content.
Shambler Enemy (ground zombie) | Enemies | In Progress | A ground zombie that wanders, spots the player, screams, chases and swipes; built but needs in-level placement and tuning.
Additional Creature Roster | Enemies | Planned | Planned new monster types (blind monster, slime, brute) to expand variety; assets chosen but not yet built.
Environmental Hazards (tentacles/biomass) | Enemies | Planned | Planned area-denial hazards and fleshy environment dressing that damage the player on contact; not yet built.
Briefcase / Player Storage | Inventory | Done | A personal storage container the player accesses across levels to stash gear they cannot carry.
Inventory System (grid) | Inventory | Done | Resident-Evil-style grid inventory holding weapons, ammo, key items and documents, with quick-slot weapon switching.
Loot Search (furniture/fixtures) | Inventory | Done | Player can search desks, lockers, drawers and bins in the world to find loot.
Notes & Documents | Inventory | Done | Found documents and clues are permanently collected and readable in a dedicated notes tab.
Save / Load System | Save | Done | Player can save and load progress across five slots, each with a screenshot, location, playtime and date.
Save Point Terminal | Save | Done | Interactable computer terminals in the world let the player manually save their game.
Interaction & Pickup System | Interaction | Done | Player can look at objects, see a prompt, and pick up, examine, or use items and devices in the world.
Key & Locked Door System | Interaction | Done | Player finds keycards and uses card readers to unlock doors and gates, gating progress.
Vent / Barricade Panels | Interaction | Done | One-time openable vents or boards that require a specific item, letting the player open new paths.
Combination Locks & Keycard Clearance | Interaction | Planned | Planned safes opened by found codes and tiered keycards that gate areas by clearance level; not yet built.
Level Transit / Travel System | Objectives | In Progress | Lets the player travel between levels and arrive at the right spot; backend built, in-level panels still being placed.
Objective / Progression System | Objectives | In Progress | Tracks the player's current goals and sub-tasks on the HUD; system works but real campaign objectives still need authoring.
NPC Dialogue & Lip Sync | Dialogue | Done | Player can talk to characters who face the player, gesture and move their mouths to voice lines.
Ambient / Atmosphere Audio | Audio | Done | Background music and horror atmosphere play at sparse intervals to build tension, plus creature and interaction sounds.
Signal Sense (radio danger warning) | Audio | Done | A radio-style danger sense that escalates audio, an on-screen waveform and controller rumble as threats or void zones get closer.
HUD (health, ammo, prompts) | UI-HUD | Done | On-screen display shows health, ammo count, and interaction prompts in a minimal horror style.
Main Menu & Pause/Settings Menu | UI-HUD | Done | Title screen with continue/load/new game, plus an in-game pause menu with audio, control and display settings.
In-Game Map System | Map | In Progress | Floor-plan maps the player picks up per area and views on a menu; system built, per-floor maps still being generated.
Lighting & Atmosphere | Lighting | Done | Dark horror lighting with flicker and shadow used as tension, tuned to avoid visual artifacts.
Background Environment (campus at night) | Lighting | Planned | Visible outdoor research campus at night through the building windows; planned, not yet built.
Character Creation Pipeline | Tooling | Done | A tool to design and save custom human appearances (the player, NPCs, extras, corpses) for use in levels.
Performance Optimization | Tooling | In Progress | Behind-the-scenes work to keep large levels running smoothly; major gains made, ongoing per-level.

## Open Work & Risks
OPEN WORK & RISKS — current tickets, blockers and production risks
TOP PRODUCTION RISKS
• First-person body clipping (seeing through your own body looking down) has resisted multiple attempts; latest engine fix is still unverified and could need more rework.
• Camera gets yanked during dodge, block, and auto-equip; a swap attempt failed and reverted, so the root cause is still unknown.
• Heavy backlog of new content (4+ creature types, outdoor environment, briefcase/safe/keycard systems, dialogue UI, per-floor maps) for a solo developer is a large schedule risk.
• Inventory storage feature has a critical defect (briefcases don't share contents) plus weapon-unequip and interaction bugs, undermining a core gameplay loop.
• Enemies cannot open doors, which can stall encounters and break pacing until proper door-handling AI is built.
• A past GPU crash was mitigated by config flags only; if it recurs the fallback is a graphics-driver swap, an external dependency.
• Many recent fixes are coded but awaiting hands-on playtest verification, so true done-state of player feel is uncertain.
BLOCKERS
• Cannot make a Blueprint override an inherited function through the automation tool (blocks one camera fix path)
• Cannot reliably preset object-reference values through the automation tool
• Floating-cube particle effect can't be finished by script; the effect editor's renderer must be edited by hand
• Engine version drift: recent notes mix 5.7 and 5.8; all builds must standardize on the current 5.8 engine to avoid stale binaries
OPEN ITEMS
Item | Priority | Area | Note
Shared briefcases don't share contents in a level | CRITICAL | Gameplay | Items put in one briefcase don't appear in another in the same level; core promise of the storage feature is broken.
Outdoor night campus visible through Building 1 windows | HIGH | Level Design | The first office building floats in black emptiness; needs a believable nighttime research campus outside the windows.
New monster: Blind Monster (ground stalker) | HIGH | Enemies | A new ground creature is planned but not started; only its art asset is on hand.
New monster: Oozling slime (fast swarm fodder) | HIGH | Enemies | A fast slime enemy is planned but not started; art asset purchased, no behavior built yet.
Validate melee pipe feel in playtest | HIGH | Combat | Melee swing was rebuilt and grip realigned but never confirmed in play; grip, swing, and damage timing need a hands-on check.
Confirm first-person body no longer shows insides when looking down | HIGH | Player | New engine fix is in but unverified; player may still see through their own body while reloading, swapping, or swinging.
Generate pickup-able floor maps for every Building 1 floor | HIGH | Level Design | Per-floor in-game maps not yet produced; pipeline exists but must be run on each floor.
Player storage briefcase (carry-vs-leave inventory) | HIGH | Gameplay | Cross-level personal storage container with limited space is planned but not built.
Fix pistol unreachable via number-key hotkey | HIGH | Combat | The starting pistol can't be selected by its quick-slot key because its slot number never gets assigned.
Final ship polish pass | HIGH | Production | Strip debug overlays, hit stable 60 FPS, full crash/softlock playthrough, screen-effect and input feel polish before release.
Equipped weapon stays active when stored in container | HIGH | Gameplay | Putting your held gun into a case leaves it still in your hands and usable; should unequip.
Adjacent loot lockers/items hard to interact with | HIGH | Gameplay | Lockers placed side by side, and some ground pickups, only respond when standing right on top of them.
Finish creature 'void ink' look across all monsters | MEDIUM | Art | Dark unified creature skin is partly done; still needs final hookup and monster variants created.
Environmental hazards: grasping tentacles and fleshy biomass | MEDIUM | Level Design | Area-denial hazards and gory set dressing for infected zones are planned but not built.
Custom-styled dialogue box for conversations | MEDIUM | UI | Conversations still use the plugin's placeholder demo box; needs the game's own horror-styled dialogue UI.
Combination safes with codes found in notes | MEDIUM | Gameplay | Lockable safes opened by codes from collected notes are planned, not started.
Tiered keycard security doors (clearance 1-5) | MEDIUM | Gameplay | Higher-clearance keycards opening lower-level doors is planned; needs a real change to how readers check cards.
Brute heavy enemy (deferred) | MEDIUM | Enemies | Large tanky enemy postponed until a suitable model is sourced; revisit after other creatures are in.
Confirm Shambler zombie stops drifting during idle | MEDIUM | Enemies | Idle-freeze fix is in code but not yet playtested; zombie should hold still and not creep while idling.
Enemies can't open doors | MEDIUM | Enemies | Monsters get stuck at closed doors; current fix only sends them back to patrol, doesn't let them through.
Building 1 room doors stopped opening | LOW | Level Design | Office room doors baked into walls no longer auto-open after the new door system; cosmetic, low priority.
Finish floating black 'void' particle effect | LOW | Art | Atmospheric floating cubes effect is half-built; final step must be done by hand in the effects editor.
Headless shadow on player | LOW | Art | Player's cast shadow has no head because the body model lacks head geometry; cosmetic.
Polish: NPC mouth/lip movement | LOW | Audio | Talking jaw works; finer lip motion is subtle and needs a tuning pass; pre-release polish.
Polish: grenade throw animation | LOW | Combat | Grenade throwing works functionally; the throw animation needs a polish pass.

## Legend & Method
HOW TO READ THIS WORKBOOK
Done | Built and functional in the project; only a formal QA play-test pass remains.
In Progress | Partially built or actively being worked; has known gaps.
Needed | Does not exist yet — gated on future work (shown as 'Not Built' for systems).
Planned | On the roadmap / ticketed but not started (systems inventory only).
N/A | Intentionally not part of this game's design (e.g. RPG relationship points, NPC daily schedules).
METHOD & CAVEATS
• Tabs: Executive Summary (the 30-second read) · Functionality Scope (the 73 capability checks from the QA list, graded project-wide) · Systems Readiness (the full feature inventory) · Open Work & Risks (tickets/blockers in plain English).
• Source: derived from the QA checklist tabs plus a verification pass over the project's source code, design docs, and session checkpoints on 2026-06-23.
• IMPORTANT — 'Built' is not 'Tested': statuses describe what exists in the build. No formal end-to-end QA playthrough has been run yet, so even 'Done' items still need a play-test confirmation.
• The per-level QA checklist (Research Facility, Office Space, Water Treatment, Sewer Tunnels, Remote Underground, END) is intentionally NOT scored here — this workbook is a project-wide functionality scope, not a per-level test log.
• Scope notes for a horror title (RE / Dead Space / Silent Hill lineage): there is no XP/leveling or RPG relationship system by design; 'progression' here means inventory, item use, and save/load — all of which are present.